## Marketing Calendar
Date | Day | Content | Type | Platform | Platform | Status | Owner | Feature | Feature Type | Approval Status | comment | Link
Monday (June 29) – Sunday (July 5)
2026-06-30 | Tuesday | PAISA BOLTA HAI: Where does ₹500/day actually go? | Content | Instagram | Instagram | In Progress | Samriddhi | Knowledge Post | External post | Approved | content ready; to be posted | https://www.instagram.com/p/DaxQrxhmVVr/?img_index=1
2026-07-01 | Wednesday | Research 360 kite teaser vid (55sec-60sec) | Content | whatsapp update group/youtube | Whatsapp Update, Youtube | Done | Charu | Research 360 | Feature post | Approved | done | https://youtu.be/Vx9fYX_Yi7k?si=3m0-i5kMWU8SFA9n
2026-07-01 | Wednesday | Research 360 Loom video ( full explainer) | Content | whatsapp update group/youtube | Whatsapp Update, Youtube | Done | Samriddhi | Research 360 | Feature post | Approved | done | https://www.loom.com/share/e41af4e54ed941cb85bb28278659987d
2026-07-01 | Wednesday | Transaction Module is live | Content | WhatsApp/yt | Whatsapp Update, Youtube | Done | Charu | Transaction Module Wylth 2.0 | Feature post | Approved | done | https://youtu.be/-8oW2QvgR88?si=xoPOUZcXWq-L2RlY
2026-07-02 | Thursday | Transaction Module Explainer | Content | whtsapp/yt | Whatsapp Update, Youtube | Done | Mahek | Transaction Module Wylth 2.0 | Feature post | Approved | done | https://youtu.be/Iuli-YEXqcg?si=7IdgRfr_N1rFsEbp
2026-07-02 | Thursday | Activation — place your first bulk order in 60 seconds/Transaction Module | Campaign | Customer.io | Customer.io | Done | Mahek | Transaction Module Wylth 2.0 | Feature post | Approved | sent
2026-07-02 | Thursday | Research 360 launch mail | Campaign | Customer.io | Customer.io | Done | Charu | Research 360 | Feature post | Approved | done
2026-07-02 | Friday | What the Wylth: Mutual Funds for Dummies | Content | Instagram | Instagram | Done | Samriddhi | Knowledge Post | External post | Approved | change of plans
Monday (July 6) – Sunday (July 12)
2026-07-06 | Monday | Rebalancing – why MFDs don't do it enough | Content | LinkedIn | Linkedin | Done | Mahek | Knowledge Post | External post | Approved | content posted | https://www.linkedin.com/posts/wylth_mutualfunds-mfd-wealthmanagement-activity-7479774344181751808-IEmQ?utm_source=share&utm_medium=member_desktop&rcm=ACoAADkA5NABgqVmgR5RnEPv0Rin9OwuWK-nIok
2026-07-07 | Tuesday | Partner success story | camoaign | update/linkedin | Whatsapp Update, Linkedin | Done | Charu | Others | Internal post | Approved | content posted | https://www.linkedin.com/posts/wylth_activity-7480488582156009472-FnpK?utm_source=share&utm_medium=member_desktop&rcm=ACoAADkA5NABgqVmgR5RnEPv0Rin9OwuWK-nIok
2026-07-07 | Tuesday | Partner success story(Hiren) | camoaign | update/linkedin | Whatsapp Update, Linkedin | Done | Charu | Others | Internal post | Approved | content posted | https://www.linkedin.com/posts/wylth_activity-7480594040233582592-4F0O?utm_source=share&utm_medium=member_desktop&rcm=ACoAADkA5NABgqVmgR5RnEPv0Rin9OwuWK-nIok
2026-07-07 | Tuesday | FD & Pre-IPO Loom Video campaign | Campaign | Customer.io | Customer.io | Done | Charu | FD, Pre-IPO | Feature post | Approved | campaign launched | https://youtu.be/Rayh8ZOflMg?si=ewr7T99MW42FuuBU
2026-07-07 | Tuesday | Carousel post on Payday effect | content | instagram | Instagram | Done | Samriddhi | Knowledge Post | External post | Approved | posted | https://www.instagram.com/p/Dae4_oSmTDE/?img_index=1
2026-07-08 | Wednesday | Why only equity funds? MF share breakdown | Content | LinkedIn | Linkedin | Done | Mahek | Knowledge Post | External post | Approved | content posted | https://www.linkedin.com/posts/wylth_mutualfunds-equityfunds-sip-activity-7481225080522330112-Vi9P?utm_source=share&utm_medium=member_desktop&rcm=ACoAADkA5NABgqVmgR5RnEPv0Rin9OwuWK-nIok
2026-07-09 | Thursday | Poll for features - Transaction module and research 360 | Content | Whatsapp update group | Whatsapp Update | Done | Charu | Transaction Module Wylth 2.0 | Feature post | Approved | posted | SCR-20260715-moyn.png
2026-07-09 | Thursday | Blog posting for brand promotion ( top 10 or smthg) | Content | Blog | Linkedin | Done | Mahek | Knowledge Post | Internal post | Approved | will be posted as blog on website
2026-07-10 | Friday | Daily digest Kite teaser creation | Content | Update/customer.io | Whatsapp Update, Customer.io | Done | Charu | Daily Digest Emailer | Feature post | Approved |  | Daily Digest Draft teaser.mp4
2026-07-10 | Friday | Instantly campaign for Research 360 | campaign | instantly | Instantly | Done | Charu | Research 360 | Feature post |  | campaign launched
2026-07-10 | Friday | Daily digest Flyer WA | campaign | Whatsapp update group | Whatsapp Update | Done | Charu | Daily Digest Emailer | Feature post | Approved |  | WhatsApp Image 2026-07-10 at 09.35.47.jpeg
2026-07-10 | Friday | Indore Launch Teasers | Campaign |  | Instagram | Done | Samriddhi | Others | Internal post | Approved |  | WhatsApp Video 2026-07-13 at 12.13.20.mp4
2026-07-10 | Friday | Instagram carausel post on MFD | content | instagram | Instagram | Done | Samriddhi | Knowledge Post | External post | Approved |  | TIPS OR TRAPS (1).pdf
Jul 13- Jul 18
2026-07-13 | Monday | Portfolio IQ Loom | Content | loom vid/yt | Youtube, Whatsapp Update | Done | Mahek | Portfolio IQ | Feature post | To be approved |  | https://www.loom.com/share/11c2e55f73284fc893c424b7ec7ecd48
2026-07-13 | Monday | Short video- How to create a client pitch report in wylth AI | Internal Prep | youtube | Youtube | Done | Charu | Wylth AI | Feature post | To be approved |  | https://kite.video/share/3GGzyT6qYks
2026-07-14 | Tuesday | LinkedIn Post – The real cost of waiting to start SIPs | Content | Linkedin | Linkedin | Done | Mahek | Knowledge Post | External post | To be approved |  | SIP Waiting_Linkedin Post.docx
2026-07-08 | Wednesday | Domestic v/s international market FD rates comparison | Content | Linkedin | Linkedin | Carryfoward | Mahek | Knowledge Post | External post | To be approved |  | FDs Comparison.docx
2026-07-15 | Wednesday | Posting "saving is not equal to financial goal | Carousel | instagram | Instagram | Done | Samriddhi | Knowledge Post | External post | To be approved |  | saving ≠ a goal.pdf
2026-07-15 | Wednesday | Breaking it Down W WYLTH : SIP vs Lump Sum in Equity – Which One Should You Choose? | REEL | Instagram | Instagram | Done | Samriddhi | Knowledge Post | External post | To be approved |  | https://drive.google.com/file/d/1rzvVqTS2uDQwyPcN2DA0_wXmH6BepoKX/view?usp=sharing
2026-07-15 | Wednesday | Onboarding Form (Website Readiness) Loom | Content | youtube/updates | Whatsapp Update, Youtube | In Progress | Mahek | Wylth Studio | Feature post | To be approved |  | https://www.loom.com/share/114dcd296fc14361a5f63a0701d6c21c
2026-07-15 | Thursday | Investor App Transaction Module - teaser video creation (short kite-style) | Teaser Video | update grp/linkedin/youtube | Whatsapp Update, Linkedin, Youtube | In Progress | Charu | Investor App Transaction Module | Feature post | in progress
2026-07-16 | Thursday | Investor App Transaction Module Flyer for promotion on updates group | campaign | Whatsapp Update | Whatsapp Update | In Progress | Charu | Investor App Transaction Module | Feature post | in progress
2026-07-16 | Thursday | LinkedIn Post – Indore Launch Event Post | Content | Linkedin | Linkedin | In Progress | Charu | Others | Internal post | Approved
2026-07-17 | Friday | Investor App Transaction Module Instantly Campaign | campaign | Instantly | Instantly | In Progress | Charu | Transaction Module Wylth 2.0 | Feature post | in progress
2026-07-17 | Friday | Investor App Transaction Module - Customer.io email campaign setup draft | Email Campaign | customer.io | Customer.io | In Progress | Charu | Investor App Transaction Module | Feature post | in progress
2026-07-17 | Friday | Investor App Transaction Module Linkedin Post (would be posted on release date) | campaign | Linkedin | Linkedin | In Progress | Charu | Investor App Transaction Module | Feature post | in progress
2026-07-17 | friday | Paisa Bolta Hai - Inflation: The Silent Tax on Your Savings Account | Carousel | instagram | Instagram | Done | Samriddhi | Knowledge Post | External post | To be approved
2026-07-17 | Friday | Loom – Investor Portal Transaction Module | Content | yt/updates | Whatsapp Update, Youtube | - | Mahek | Knowledge Post | Feature post | in progress
2026-07-17 | Friday | Breaking It Down w Wylth : What is a SIP, actually? | REEL | Instagram | Instagram | In Progress | Samriddhi | Knowledge Post | External post | in progress
2026-07-18 | Saturday | LinkedIn Post – How SIPs are about automating market behaviour | Content | Linkedin | Linkedin | - | Mahek | Knowledge Post | External post | in progress
Jul 20- Jul 25
2026-07-20 | Monday | Loom – MF Brokerage Report | Content | yt/updates | Whatsapp Update, Youtube | - | Mahek | MF Brokerage Report | Feature post | in progress
2026-07-20 | monday | MF Brokerage - Customer.io email campaign setup draft | customer.io | customer.io | Youtube | - | Charu | MF Brokerage Report | Feature post | in progress
2026-07-20 | Monday | MF brokerage Linkedin Post (would be posted on release date) | Linkedin | Linkedin | Linkedin | - | Charu | MF Brokerage Report | Feature post | in progress
2026-07-20 | Monday | Paisa Bolta Hai - Your First Job vs Your First Investment — Why There's a Gap? | Carousel | instagram | Instagram | - | Samriddhi | Knowledge Post | External post | in progress
2026-07-21 | Tuesday | LinkedIn Post – XIRR | Content | Linkedin | Linkedin | - | Mahek | Knowledge Post | External post | in progress
2026-07-21 | Tuesday | What is ELSS? The Only Mutual Fund With a Lock-In (and Why) | REEL | instagram | Instagram | - | Samriddhi | Knowledge Post | External post | in progress
2026-07-21 | Tuesday | Paisa Bolta Hai - Good Debt vs Bad Debt — What's the Actual Difference? | Carousel | instagram | Instagram | Done | Samriddhi | Knowledge Post | External post | to be approved
2026-07-22 | Wednesday | MF Brokerage Instantly Campaign | campaign | instantly | Instantly | - | Charu | MF Brokerage Report | Feature post | in progress
2026-07-22 | Wednesday | MF Brokerage Module - teaser video creation (short kite-style) | Kite | yt/updates/linkedin | Whatsapp Update, Youtube, Linkedin | - | Charu | MF Brokerage Report | Feature post | in progress
2026-07-22 | Wednesday | MF Brokerage Flyer for promotion on updates group | content | updates | Whatsapp Update | - | Charu | MF Brokerage Report | Feature post | in progress
2026-07-22 | Wednesday | Paisa Bolta Hai - Why UPI Makes You Spend More Without Realizing It | Carousel | instagram | Instagram | Done | Samriddhi | Knowledge Post | External post | to be approved
2026-07-23 | Thursday | LinkedIn Post – STP + SWP | Content | Linkedin | Linkedin | - | Mahek | Knowledge Post | External post | in progress
2026-07-23 | Thursday | STP Explained: Moving Money Without Moving Yourself | REEL | instagram | Instagram | - | Samriddhi | Knowledge Post | External post | in progress
2026-07-23 | Thursday | Paisa Bolta Hai - What Does an MFD Actually Do? (It's Not Just 'Selling Funds') | Carousel | instagram | Instagram | - | Samriddhi | Knowledge Post | External post | in progress
2026-07-24 | Friday | Loom – Client Churn Predictor | Content | yt/updates | Youtube, Whatsapp Update | - | Mahek | wylth 2.0 internal features | Feature post | in progress
2026-07-25 | Saturday | LinkedIn Post – Research 360 | Content | Linkedin | Linkedin | - | Mahek | Research 360 | Feature post | in progress

## Tasksheet(All)
Task | Type | Task Type | Status | Priority | Due Date | Notes
Jun 29 – July 5
Rebalancing LinkedIn post | Content | Marketing task | Done | High | 2026-07-02 |  | Mahek
Why only equity LinkedIn post — MF share breakdown + psych | Content | Marketing task | Carryfoward | Medium | 2026-07-03 | awaiting approval
Research Syfe, Altruist, Infinyte Club | Research | Product Task | In Progress | Low | 2026-07-05 | create report
Top 10 MFD software research | Product | Marketing task | Carryfoward | High | 2026-07-05
SQL review and identify 10 queries | Skill Building | Product Task | Done | Medium | 2026-07-05 | collaborate with winston
Transaction Module is live | Content | Marketing task | Done | High | Wednesday |  | Charu
Transaction Module teaser video | kite video | Marketing task | Done | High | Wednesday
Research 360 kite launch video | kite video | Marketing task | Done | High | Wednesday
Blog for FD promotion | blog/article | Marketing task | Done | High | Wednesday
Research 360 launch mail | Customer.io | Marketing task | Done | High | Thursday
Transaction module launch mail | Customer.io | Marketing task | Done | Medium | friday
Research about MFDs and the industry | Research | Product Task | Done | Low | tuesday |  | Samriddhi
Recording LOOM video (Research 360 walkthrough) | Linkedin | Marketing task | Done | Medium | wednesday
Formulate a content book | Internal Prep | Marketing task | Done | High | friday
July 6 – July 12
Draft blogpost outline, Wylth #1 | Content | Marketing task | In Progress | Medium | 2026-07-06 | will be posted as blog/linkedin | Mahek
New LinkedIn Post - topic equities MF | content | Marketing task | In Progress | Medium | 2026-07-07 | content finalized by tuesday
Domestic v/s international market FD rates comparison | Content | Marketing task | To Do | Medium | 2026-07-08 | polished report
Wylth AI workflow rethink | Internal | Product Task | To Do | Medium | 2026-07-09 | collaborate with akshit
Research 360 Success Flyer | Content | Marketing task | In Progress | Medium | 2026-07-08 | Highlight Research 360 launch success flyer. | Charukant
Portfolio IQ Kite teaser | Content | Marketing task | In Progress | High | 2026-07-08
FD & Pre-IPO Loom Video campaign | customer.io | Marketing task | Done | Low | 2026-07-07 | Loom video email explaining FD and Pre-IPO.
Research 360 Linkedin Post | linkedin | Marketing task | In Progress | Medium | 2026-07-09
Portfolio IQ customer.io campaign | customer.io | Marketing task | In Progress | Medium | 2026-07-09
Poll for features - Transaction module and research 360 | update grp | Marketing task | Done | Medium | 2026-07-09
Revamped UI for FD | internal | Product Task | To Do | Medium | 2026-07-08 | create a revamped ui based on the friction points present in current version
Filming Content For DW Ep 2 | Instagram | Marketing task | Done | Medium |  | Internal Prep | Samriddhi
Decoding Wylth E3 : SIP your Money? | Instagram | Marketing task | To Do | Medium |  | Financial Literacy Content
Filming Content For WHY WYLTH EXISTS? | Instagram | Marketing task | In Progress | High |  | Internal Prep
Indore office | content | Marketing task | Done | Low | 2026-07-10 | content slideshow for indore office
Analysis of Wylth AI subscriptions and AI assets usage | internal | Product Task | Done | High |  |  | Winston
Queries for Holding Cost & Current Value computation (Portfolio IQ) | internal | Product Task | Done | Medium
MixPanel tracking — Pre-IPO & FD clicks (Client App + Partner App) | internal | Product Task | Done | Medium
Clean raw data, add metrics & share with Customer Success team | internal | Product Task | Done | High
Wylth DB visualizations and structure documentation | internal | Product Task | Done | High
Fixxera data mapping and understanding in the Data Base | internal | Product Task | In Progress | High
AI Assets usage deep-dive & document WhatsApp sharing flow | internal | Product Task | Done | Medium
July 13 – July 18
Portfolio IQ Loom | Content | Marketing task | To Do | High | 2026-07-13 |  | Mahek
Daily digest loom | content | Marketing task | To Do | High
LinkedIn Post – The real cost of waiting to start SIPs | Content | Marketing task | To Do | Medium | 2026-07-14 | what ₹10,000 SIP at 25 vs 30 vs 35 actually becomes
LinkedIn Post – What your AUM statement doesn't tell you about your business | Content | Marketing task | To Do | Medium | 2026-07-15
LinkedIn Article – MFD business/how to start MFD practice | Content | Marketing task | To Do | Medium | 2026-07-16 | data-focused
Short video- How to create a client pitch report in wylth AI | Internal Prep | Marketing task | To Do | Medium |  |  | Samriddhi
Posting "How to book FD through WYLTH?" | Shorts | Marketing task | To Do | High
Curating the carousel post for PAISA BOLTA HAI | Carousel | Marketing task | Done | High
SIP vs LUMP SUM | Reel | Marketing task | Done | High
Report Builder - teaser video creation (short kite-style) | Teaser Video | Marketing task | To Do | High | Monday | will prepare the content ...will upload when the launch date is revealed | Charukant
Report Builder - Customer.io email campaign setup draft | Email Campaign | Marketing task | To Do | Medium | monday | will prepare the content ...will upload when the launch date is revealed
Report Builder - WhatsApp update group message creation | Group Message | Marketing task | To Do | High | Tuesday | will prepare the content ...will upload when the launch date is revealed
LinkedIn post - Report Builder launch announcement draft | LinkedIn Post | Marketing task | To Do | High | tuesday | will prepare the content ...will upload when the launch date is revealed
Wylth Studio -handover documentation & status sync | Internal | Product Task | To Do | High | wednesday/thursday | will coordinate with akshit
Connected with Akshit and made a plan and sketch for potential Whatsapp feature to share Wylth AI Assets | Internal | Product Task | In Progress | High
Daily Digest Emailer — teaser video (short kite-style) | Teaser Video | Marketing task | To Do | High
Daily Digest Emailer — Customer.io email campaign setup | Email Campaign | Marketing task | To Do | High
Daily Digest Emailer — WhatsApp update group message | Group Message | Marketing task | To Do | High
LinkedIn post — Daily Digest Emailer teaser / pre-launch | LinkedIn Post | Marketing task | To Do | High
Made 10 custom queries to generate data for different important Data Metrics related to Transactions and Partner Logins | Internal | Product Task | In Progress | Medium |  |  | Winston · Mahek
Connected with Akshit and made a plan and sketch for potential Whatsapp feature to share Wylth AI Assets | Internal | Product Task | In Progress | Medium |  |  | Winston · Akshit
Use the queries generated to make attractive visuals which are to be used for Interactive LinkedIn Posts | Internal | Product Task | In Progress | Medium |  |  | Winston · Mahek
Discuss and make a proper Documentation for Wylth AI Whatsapp feature along with a draft design with Akshit | Internal | Product Task | In Progress | Medium |  |  | Winston · Akshit
Aamir Deliverables
Jun 29 – July 3
Daily marketing creatives ( Pre IPO, FD + Wylth AI ) | Creatives |  | Done | 5 | 6
Branded creatives for partners ( Pre-IPO & FD ) | Creatives |  | Done | 50 | 50
Wylth AI Image | Creatives |  | Done | 10 | 10
Wylth AI Videos | Creatives |  | Carryfoward | 10 | 7 | 3 Carryforward to next week
July 6 – July 12
Daily marketing creatives ( Pre IPO, FD + Wylth AI ) | Creatives |  | In Progress | 5 | 3
Branded creatives for partners ( Pre-IPO & FD ) | Creatives |  | In Progress | 50 | 15
Wylth AI Image | Creatives |  | In Progress | 10 | 4
Wylth AI Videos | Creatives |  | In Progress | 13 | 6
Short form videos & Demos | Creatives |  | In Progress | 3 |  | Pre-IPO, SIP vs Lump sum - Reel, Demo - Wylth AI
July 13 – July 18
Daily marketing creatives ( Pre IPO, FD + Wylth AI ) | Creatives |  | To Do | 5
Branded creatives for partners ( Pre-IPO & FD ) | Creatives |  | To Do | 50
Wylth AI Image | Creatives |  | To Do | 10
Wylth AI Videos | Creatives |  | To Do | 13
Short form videos & Demos | Creatives |  | To Do | 3

## RequestsModifications to be mad
Content | Type | Date | Changes/Additions to be made | Charu
Partner success story | June FD campaign | 2026-02-07 | WA flayer for wylth update, LinkedIn Post | Charu | Ashu
Tranx teaser video
Report Builder Teaser video
Indore launch teasers |  | 2026-08-07 |  | Samriddhi
Partner success story | July FD campaign | July Month | WA flyer to promote partner if partner completes 3 FDs |  | Ashu
Partner success story | July FD campaign | 1st Week Aug | WA flayer for wylth update, LinkedIn Post if partner completes 10 FDs |  | Ashu

## Tasks – Mahek
Task | Type | Status | Priority | Due Date | Notes
Jun 22 – Jun 28
Wylth Studio onboarding form, 44-question Tally form | Content | Done |  | -
Loom video – Transaction Module | Content | Done |  | -
Loom video – Pre-IPO and FD | Content | Done |  | -
Loom video – Onboarding Form | Content | Done |  | -
Global MFD model benchmarks | Research | Done |  | - | researched MFD models in UK, Aus, China, US
New-age B2C platform study | Research | Done |  | - | researched what's working for groww, kuvera, indmoney, zerodha
Jun 29 – July 5
Rebalancing LinkedIn post | Content | Done |  | 2026-07-02
Why only equity LinkedIn post — MF share breakdown + psych | Content | Done |  | 2026-07-03 | awaiting approval
Research Syfe, Altruist, Infinyte Club | Research | Carryfoward | Low | 2026-07-05 | create report
Top 10 MFD software research | Product | Done | High | 2026-07-05
SQL review and identify 10 queries | Skill Building | Done | Medium | 2026-07-05 | collaborate with winston
July 6 – July 12
Draft blogpost outline, Wylth #1 - LinkedIn + website blog | Content | Done | High | 2026-07-06
Exploring syntax for 10 SQL queries | Skill Building | Done | Medium | 2026-07-07 | collaborate with winston
LinkedIn Post – T30 vs B30 transaction data — Wylth's B30 onboarding story | Content | Done | High | 2026-07-08 | cancelled
Wylth AI workflow rethink | Internal | Done | Medium | 2026-07-09 | collaborate with akshit + winston
Research Syfe, Altruist, Infinyte Club | Research | In Progress | Medium | 2026-07-11 | create report
Domestic v/s international market FD rates comparison - LinkedIn post | Content | Done | Medium | 2026-07-12 | rework in progress
July 13 – July 19
Portfolio IQ Loom | Content | Done | High | 2026-07-13
LinkedIn Post – The real cost of waiting to start SIPs | Content | Done | High | 2026-07-14 | awaiting approval
Onboarding Form (Website Readiness) Loom | Content | In Progress | High | 2026-07-15
LinkedIn Post – Portfolio IQ | Content | Done | High | 2026-07-16 | awaiting approval
Wylth AI Marketing Assets Loom | Content | To Do | High | 2026-07-17
Wylth AI Pitch Report Loom | Content | To Do | High | 2026-07-17
LinkedIn Post – How SIPs are about automating market behaviour | Content | To Do | High | 2026-07-18
July 20 – July 26
Loom – MF Brokerage Report | Content | To Do | High | 2026-07-20
LinkedIn Post – XIRR | Content | To Do | High | 2026-07-21
Loom – Investor Portal Transaction Module | Content | To Do | High | 2026-07-22
LinkedIn Post – STP + SWP | Content | To Do | High | 2026-07-23 | most ppl know about SIP but not the other two
Loom – Client Churn Predictor | Content | To Do | High | 2026-07-24
LinkedIn Post – Research 360 | Content | To Do | High | 2026-07-25 | feature explanation + utility

## Tasks – Charu
Date | Date | Topic | Type | Status | Priority | Notes | work approval
jun28- jul 5
Wednesday | Transaction Module is live | Content | WhatsApp | Done | High
Wednesday | Transaction Module teaser video | kite video | whatsapp/youtube | Done | High |  |  | asked sachin for the documentation
Wednesday | Research 360 kite launch video | kite video | whatsapp/youtube | Done | High
Wednesday | Blog for FD promotion | blog/article | linkedin | Done | High
Thursday | Research 360 launch mail | Customer.io |  | Done | High
Thursday | Transaction module launch mail | Customer.io |  | Done | Medium
jul 5- jul 12
Tuesday | Partner success story | campaign | update/linkedin | Done | High
Wednesday | Portfolio IQ Kite teaser creation | Content | Update/customer.io | In Progress | Medium
Wednesday | Portfolio IQ customer.io campaign | campaign | Customer.io | In Progress | Medium
Thursday | Poll for features - Transaction module and research 360 | Content | Whatsapp update group | To Do | Medium
Thursday | Research 360 Success Flyer | Content | WhatsApp | To Do | Medium
Thursday | Portfolio IQ - WhatsApp update group message draft | Group Message | WhatsApp | To Do | High
Thursday | Research 360 Success Flyer | Content | WhatsApp | To Do
friday | LinkedIn post — Portfolio IQ teaser / pre-launch | LinkedIn Post | LinkedIn | To Do
Jul 12- Jul 19
Monday | Report Builder - teaser video creation (short kite-style) | Teaser Video | WhatsApp / YouTube | To Do
monday | Report Builder - Customer.io email campaign setup draft | Email Campaign | Customer.io | To Do
Tuesday | Report Builder - WhatsApp update group message creation | Group Message | WhatsApp | To Do
tuesday | LinkedIn post - Report Builder launch announcement draft | LinkedIn Post | LinkedIn | To Do
wednesday/thursday | Wylth Studio -handover documentation & status sync | Internal |  | To Do

## Tasks - Akshit
Task | Type | Status | Priority | Due Date | Notes
Jun 22 - Jun 26
Firestore data collection - started | Research | Done | High | 2026-06-22 | Pulling all onboarding form responses received via email from Firestore
Firestore data collection - completed | Research | Done | Medium | 2026-06-23 | Finished extracting full response dataset from Firestore
Converted responses into Excel format | Research | Done | High | 2026-06-24 | Structured and cleaned data into an Excel sheet for analysis
Website templates - started | Content | Done | Medium | 2026-06-25 | Began building multiple template options for the website
Website templates - finalized | Content | Done | Medium | 2026-06-26 | Completed multiple website template variants
Jun 29 - Jul 3
Chatbot PRD - initial draft | Product | Done | Low | 2026-06-29 | Drafting the product requirements document for the main website chatbot
Chatbot demo prep + backend sync kickoff | Product | Done | Medium | 2026-06-30 | Preparing chatbot demo; kicked off templates feedback loop with backend
Templates feedback loop with backend team | Content | Done | High | 2026-07-01 | Filtering partner details for WylthAI feedback calls
Chatbot question design review | Product | Done | Medium | 2026-07-02 | Discussing chatbot questions and follow-up flows
WylthAI integration calls & Pitch Report Creation | Product | Done | High | 2026-07-03 | Wrapping up calls and pitch report
Jul 6 - Jul 10
Form Responses shifted to sheet + Dev team communication | Internal | Done | High | 2026-07-06 | Nudge RMs for High/Medium filled fields
WhatsApp Integration - requirement scoping & use-case mapping | Product | Done | Medium | 2026-07-06 | Mapping partner creative-sharing use cases for WylthAI dashboard
Wylth Studio Handoff - codebase walkthrough planning | Internal | Done | Medium | 2026-07-06 | Planning codebase walkthrough with Dev team
2 more Demo Websites for templates. | Content | Done | High | 2026-07-06 | 2 more demo websites that need to be made by the evening and to be delivered by changing the theme completely of the website.
Changes in the Wylth Studio Email Onboarding Form along with Complete % and Critical Questions | Internal | Done | High | 2026-07-07
WhatsApp Integration - API documentation review | Product | Done | High | 2026-07-07 | Reviewing WhatsApp Business API docs
Wylth Studio Handoff - codebase access & env setup | Product | Done | Medium | 2026-07-07 | Setup with Dev team (Aman Jain, Saurabh)
WhatsApp Integration - PRD documentation drafting | Product | Done | High | 2026-07-08 | Drafting PRD documentation and integration approach
Wylth Studio Handoff - security rules & final migration checklist | Internal | Done | High | 2026-07-08 | Firestore/Firebase security rules review; finalizing migration checklist
WhatsApp Business integration - dev start | Product | Done | Medium | 2026-07-09 | Beginning development in WylthAI dashboard
Wylth Studio Handoff - final handoff to Dev Team | Internal | Done | High | 2026-07-09 | Completing handoff of website/forms codebase and security
WhatsApp Business integration - dev continued | Product | Done | Medium | 2026-07-10 | Continuing integration build for partner creative sharing
RupixFlow Website Content Changes according to Partner | Product | Done | High | 2026-07-10 | RupixFlow design was likes by one investor and needs to be handoff to Dev Team with proper content changes
Jul 13 - Jul 17
Referral (Product) - Requirements gathering & PRD kickoff | Product | To Do | High | 2026-07-13 | Structuring PRD for referral-as-a-product on Wylth Dashboard (CRM portal)
Referral (Product) - PRD drafting | Product | To Do | Medium | 2026-07-14 | Referral flow, incentive structure, tracking mechanics
Referral (Product) - PRD stakeholder review & documentation | Product | To Do | Medium | 2026-07-15 | Review with stakeholders, finalize documentation
Referral (Product) - Demo/prototype build | Product | To Do | High | 2026-07-16 | Building demo/prototype within CRM portal
Referral (Product) - Demo walkthrough, sign-off & handoff to Dev | Product | To Do | Medium | 2026-07-17 | Demo walkthrough with stakeholders, sign-off, handoff to engineering

## Tasks – Samriddhi
Task | Type | Status | Priority | Due Date | Notes
Jun 22 – Jun 28
POST Breaking it Down with WYLTH : Mutual Funds for Dummies | Reel | Done | High | - | Posted on Instagram
Paisa Bolta Hai Post - Where does 500 Rs. per day actually go? | Carousel | Done | Medium | - | con
Jun 29 – July 5
Recording LOOM video (Research 360 walkthrough) | Linkedin&YT | Done | Medium | - | discarded ; mehak to re-do
Formulate a content book | Internal Prep | Done | High
July 6 – July 12 | [5 empty] | 2026-07-15
Post the Paisa Bolta Hai : Payday post | Carousel | Done | High
Posting Breaking It down w WYLTH FIRE number | Reel | In Progress | High |  | Content Discarded
Condense the already created walkthrough videos. | Shorts | Carryfoward | Medium
Posting Paisa Bolta Hai : Tips/Traps post | Carousel | Done | Medium |  | to be approved
July 13 – July 18
Posting "How to track FD through WYLTH?" | Shorts | DISCARDED | High |  | task discarded, out of expertise
SIP vs Lump Sum in Equity – Which One Should You Choose? | Reel | Done | High |  | to be approved
Paisa Bolta Hai Post - What is a Financial Goal vs Just 'Saving'? | Carousel | Done |  |  | to be approved
Paisa Bolta Hai - Inflation: The Silent Tax on Your Savings Account | Carousel | Done | Low |  | to be approved
Breaking It Down w Wylth : What is a SIP, actually? | Reel | To Do | Low
July 20 – July 26
Paisa Bolta Hai - Your First Job vs Your First Investment — Why There's a Gap? | Carousel | To Do
Paisa Bolta Hai - Good Debt vs Bad Debt — What's the Actual Difference? | Carousel | Done |  |  | to be approved
Paisa Bolta Hai - Why UPI Makes You Spend More Without Realizing It | Carousel | Done |  |  | to be approved
Paisa Bolta Hai - What Does an MFD Actually Do? (It's Not Just 'Selling Funds') | Carousel | In Progress
Paisa Bolta Hai - What's the Actual Cost of NOT Having an Advisor? | Carousel | To Do
What is ELSS? The Only Mutual Fund With a Lock-In (and Why) | Reel | To Do
STP Explained: Moving Money Without Moving Yourself | Reel | To Do

## Tasks – Aamir
Task | Type | Status | Target | Completed | Remarks | Notes
Jun 29 – July 3
Daily marketing creatives ( Pre IPO, FD + Wylth AI ) | Creatives | Done | 5 | 6
Branded creatives for partners ( Pre-IPO & FD ) | Creatives | Done | 50 | 50
Wylth AI Image | Creatives | Done | 10 | 10
Wylth AI Videos | Creatives | Carryfoward | 10 | 7 | 3 Carryforward to next week
July 6 – July 12
Daily marketing creatives ( Pre IPO, FD + Wylth AI ) | Creatives | In Progress | 5 | 3
Branded creatives for partners ( Pre-IPO & FD ) | Creatives | In Progress | 50 | 15
Wylth AI Image | Creatives | In Progress | 10 | 4
Wylth AI Videos | Creatives | In Progress | 13 | 6
Short form videos & Demos | Creatives | In Progress | 3 |  | Pre-IPO, SIP vs Lump sum - Reel, Demo - Wylth AI
July 13 – July 18
Daily marketing creatives ( Pre IPO, FD + Wylth AI ) | Creatives | To Do | 5
Branded creatives for partners ( Pre-IPO & FD ) | Creatives | To Do | 50
Wylth AI Image | Creatives | To Do | 10
Wylth AI Videos | Creatives | To Do | 13
Short form videos & Demos | Creatives | To Do | 3 |  |  |  | Short form videos & Demos | Creatives | In Progress | Short form videos & Demos | Creatives | In Progress

## Tasks-Winston
Date | Task | Type | Owner / Collaborator | Status | Effort | Impact
Daily
Daily | Tracked and reported key business performance metrics, including Onboardings, Renewals, Wylth AI subscriptions and adoption, Pre-IPO transactions, FD/RD transactions, feature adoption, and Partner/Investor login trends across Web and Mobile platforms. | Visuals/Queries/Flash | Winston | Completed | Low | Enables management to monitor the business performance
Last Month
Last Month | Made a document for all relevant events that we have to track via Mixpanel for key metrics like AI/ FD/ Pre-IPO/ Transactions placed/Reports Viewed/Downloaded to track drop-offs and usage and shared the documentation with the relevant teams for implementation | Documentation | Winston · Sujith · Dev | In Progress | Medium | Will give a better way to monitor user journeys and track drop offs for all key features
Last Week
Last Week | Worked with Srishti on designing and validating SQL queries for Holding Cost and Current Value computation for the Portfolio IQ module. | Query/Data | Winston · Srishti | Completed | Low | Holding Cost and Current Value computation for Portfolio IQ module
Last Week | Created Mixpanel tracking reports and visual dashboards to monitor Pre-IPO and Fixed Deposit user interactions across both Client and Partner applications. | Mixpanel Visual | Winston | Completed | Low | Shows us user engagement and clicks with respect to our Pre-IPO and FD modules
Last Week | Extracted month-wise clicks data, cleaned and enhanced the dataset with relevant KPIs, and shared partner and investor wise insights with the Customer Success team to help partners understand investor engagement. | Query/Data | Winston · Ashutosh | Completed | Low | Data to be shared with Partners showing them how many of their investors are showing interest in the FD/Pre IPO modules
Last Week | Created visualizations and infographics explaining the Wylth database structure, table relationships, and overall data flow for internal reference. | Query/Data/Visuals | Winston · Mahek | In Progress | Low | Internal Knowledge Transfer
Last Week | Conducted database knowledge transfer sessions and provided Wylth database understanding to Mahek. | Query/Data | Winston · Mahek | Completed | Low | Internal Knowledge Transfer
This Week
This Week | Developed custom SQL queries to generate business metrics related to transactions, partner activity, and platform logins. | Query/Data | Winston · Mahek | In Progress | Medium | Use the data generated from queries to generate marketing/linkedin content and visuals that will improve visibility
This Week | Utilized the generated datasets to create charts, dashboards, and infographics for interactive marketing content and LinkedIn posts. | Query/Data/Visuals | Winston · Mahek | In Progress | Low
This Week | Discussed the requirement for an internal dashboard to identify partners who have completed FD/RD transactions, along with transaction counts and their assigned SRMs. | Discussion | Winston · Ashutosh | Completed | High | Provides an Internal UI for Customer Success team to track Partnerwise FD/RD transactions monthwise and RM wise
This Week | Performed an in-depth analysis of the Fixxera database and backend table mappings to understand the data flow required for the dashboard implementation. | Query/Data | Winston | Completed | Low
This Week | Identified data discrepancies, mapping gaps, and blockers during the Fixerra Dashboard data vs Wylth Database analysis, and documented them with supporting evidence before communicating them to the respective teams for resolution. | Query/Data | Winston | Completed | Medium
This Week | Collaborated with Akshith to work on a WhatsApp integration that enables partners to directly share Wylth AI-generated marketing assets with investors after asset generation. | Discussion | Winston · Akshith | In Progress | Medium | Provide an easier way for Partners to share AI Marketing assets with their clients
This Week | Prepared a documentation outlining the proposed WhatsApp feature, implementation workflow, business logic, and requirements, followed by detailed discussions with Akshith. Review Pending | Documentation | Winston | In Progress | Low